## Sheet1
Tasks | Week | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Presentation | Present | 4: YW; 10: HY + EM; 15: HY or EM + NI
| PPT | 4: YW; 10: HY + EM; 15: HY or EM + NI
GPU usage monitor | Get familiar with Ray | bar: 5 to 6
Create development environment | bar: 7 to 9
Develop distributed application | bar: 11 to 14
Meal queue | Prepare Equipment | bar: 4 to 5
Test different models | bar: 6 to 7
Develop detection pipeline | bar: 8 to 9; 11 to 14
Meal Recommendor | Gather Data | bar: 4 to 5
| Build/train recommendor system | 6: EM+NI; 7: EM+NI; 8: EM+NI; 9: EM+NI
| Develop system pipeline | 11: EM+NI; 12: EM+NI; 13: EM+NI; 14: EM+NI
Regular Meetings |  | 5: ALL; 7: ALL; 9: ALL; 12: ALL; 14: ALL
App Development | UX/UI Design | 7: YW; 8: EM; 9: YW; 11: HY; 12: YW; 13: YW; 14: ALL
| Test | 7: EM; 8: HY; 9: EM; 11: NI; 12: HY; 13: NI; 14: ALL
| Front Development | 7: NI; 8: YW; 9: NI; 11: YW; 12: EM; 13: HY; 14: ALL